## Cover
ISO/IEC 27001:2022 Gap Assessment
Annex A Control Gap Assessment & Remediation Roadmap
Client (fictional) | Meridian Analytics Ltd
Scope | Meridian Analytics' SaaS analytics platform, corporate IT, and supporting business processes (UK head office + remote workforce)
Assessment date | 2026-09-01
Assessor | Sanika Mahamulkar
Context | Meridian Analytics holds ISO/IEC 27001:2013 certification. This assessment was performed ahead of the transition audit to the 2022 revision, to identify gaps against the restructured Annex A control set before the Stage 2 transition audit.
Maturity Rating Legend
Not Implemented (0) | No control activity in place.
Ad Hoc (1) | Control activity occurs informally, with no defined process.
Partially Implemented (2) | Control is in place but incomplete, inconsistent, or not technically enforced.
Implemented - Not Reviewed (3) | Control is fully operating but has not yet had a formal effectiveness review.
Implemented - Reviewed & Effective (4) | Control is operating and has been reviewed/evidenced as effective.
Priority / Remediation SLA Legend
High | Target remediation within 60 days of assessment date.
Medium | Target remediation within 120 days of assessment date.
Low | Target remediation within 180 days of assessment date; typically a formal-review gap rather than a true control gap.
N/A - Maintain | Control is mature; no remediation required, maintain and re-review periodically.
Note
This is a self-directed portfolio project modelling a real ISO/IEC 27001:2022 Annex A gap assessment methodology against a fictional company. All findings, maturity ratings, and dates are illustrative.

## Dashboard
ISO/IEC 27001:2022 Gap Assessment - Dashboard
Total controls assessed | 93
Findings requiring action (High + Medium priority) | 17
Overall average maturity score (0-4 scale) | 3.3118
Percent of controls at maturity 3 or 4 | 81.72%
Controls by Theme and Maturity
Theme | Not Implemented | Ad Hoc | Partially Implemented | Implemented - Not Reviewed | Implemented - Reviewed & Effective
Organizational | 4 | 0 | 2 | 6 | 25
People | 0 | 0 | 1 | 1 | 6
Physical | 0 | 0 | 2 | 2 | 10
Technological | 4 | 0 | 4 | 5 | 21
Findings by Priority
Priority | Count
High | 8
Medium | 9
Low | 14
N/A - Maintain | 62

## Gap Assessment Matrix
ISO/IEC 27001:2022 Annex A - Gap Assessment Matrix (93 controls)
Control ID | Control Name | Theme | Current Maturity | Evidence / Notes | Gap Description | Priority | Target Remediation Date | Owner | Maturity Score
5.1 | Policies for information security | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Head of GRC | 4
5.2 | Information security roles and responsibilities | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Head of GRC | 4
5.3 | Segregation of duties | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Head of GRC | 4
5.4 | Management responsibilities | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Head of GRC | 4
5.5 | Contact with authorities | Organizational | Implemented - Not Reviewed | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of GRC | 3
5.6 | Contact with special interest groups | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Head of GRC | 4
5.7 | Threat intelligence | Organizational | Not Implemented |  | No formal threat intelligence process; ad hoc use of vendor security bulletins only. | High | 2026-10-31 | Head of GRC | 0
5.8 | Information security in project management | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Head of GRC | 4
5.9 | Inventory of information and other associated assets | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Head of GRC | 4
5.10 | Acceptable use of information and other associated assets | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Head of GRC | 4
5.11 | Return of assets | Organizational | Implemented - Not Reviewed | Process operating and evidenced via records reviewed during the last internal audit. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of GRC | 3
5.12 | Classification of information | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Head of GRC | 4
5.13 | Labelling of information | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Head of GRC | 4
5.14 | Information transfer | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Head of GRC | 4
5.15 | Access control | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Head of GRC | 4
5.16 | Identity management | Organizational | Implemented - Not Reviewed | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of GRC | 3
5.17 | Authentication information | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Head of GRC | 4
5.18 | Access rights | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Head of GRC | 4
5.19 | Information security in supplier relationships | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Vendor & Procurement Manager | 4
5.20 | Addressing information security within supplier agreements | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Vendor & Procurement Manager | 4
5.21 | Managing information security in the ICT supply chain | Organizational | Not Implemented |  | ICT supply chain risk is not assessed separately from general supplier due diligence. | High | 2026-10-31 | Vendor & Procurement Manager | 0
5.22 | Monitoring, review, and change management of supplier services | Organizational | Implemented - Not Reviewed | Evidenced via signed records retained in the document management system. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Vendor & Procurement Manager | 3
5.23 | Information security for use of cloud services | Organizational | Partially Implemented |  | Cloud vendor security is reviewed at onboarding only; no ongoing cloud security governance process. | Medium | 2026-12-30 | Head of GRC | 2
5.24 | Information security incident management planning and preparation | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Security Operations Lead | 4
5.25 | Assessment and decision on information security events | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Security Operations Lead | 4
5.26 | Response to information security incidents | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Security Operations Lead | 4
5.27 | Learning from information security incidents | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Security Operations Lead | 4
5.28 | Collection of evidence | Organizational | Not Implemented |  | No documented procedure for collection and preservation of evidence following a security incident. | High | 2026-10-31 | Security Operations Lead | 0
5.29 | Information security during disruption | Organizational | Implemented - Not Reviewed | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of GRC | 3
5.30 | ICT readiness for business continuity | Organizational | Not Implemented |  | ICT continuity plan not yet aligned to BIA-derived recovery time/point objectives. | High | 2026-10-31 | Head of GRC | 0
5.31 | Legal, statutory, regulatory, and contractual requirements | Organizational | Implemented - Reviewed & Effective | Process operating and evidenced via records reviewed during the last internal audit. |  | N/A - Maintain |  | Data Protection Officer | 4
5.32 | Intellectual property rights | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Legal Counsel | 4
5.33 | Protection of records | Organizational | Implemented - Reviewed & Effective | Evidenced via signed records retained in the document management system. |  | N/A - Maintain |  | Data Protection Officer | 4
5.34 | Privacy and protection of PII | Organizational | Implemented - Reviewed & Effective | Documented in the Information Security Policy Suite (v3.2); reviewed annually by the GRC team. |  | N/A - Maintain |  | Data Protection Officer | 4
5.35 | Independent review of information security | Organizational | Partially Implemented |  | Last independent ISMS review was 19 months ago; no fixed review cadence is defined. | Medium | 2026-12-30 | Head of GRC | 2
5.36 | Compliance with policies, rules, and standards | Organizational | Implemented - Not Reviewed | Process operating and evidenced via records reviewed during the last internal audit. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of GRC | 3
5.37 | Documented operating procedures | Organizational | Implemented - Reviewed & Effective | Control embedded in the ISMS Manual; last reviewed at the most recent management review meeting. |  | N/A - Maintain |  | Head of GRC | 4
6.1 | Screening | People | Implemented - Reviewed & Effective | Evidenced via HR onboarding/offboarding checklist completion records. |  | N/A - Maintain |  | HR Director | 4
6.2 | Terms and conditions of employment | People | Implemented - Reviewed & Effective | Training completion tracked in the LMS; completion rate above 95% for the last cycle. |  | N/A - Maintain |  | HR Director | 4
6.3 | Information security awareness, education, and training | People | Implemented - Reviewed & Effective | Evidenced via signed employee handbook acknowledgement on file. |  | N/A - Maintain |  | HR Director | 4
6.4 | Disciplinary process | People | Implemented - Reviewed & Effective | Evidenced via HR onboarding/offboarding checklist completion records. |  | N/A - Maintain |  | HR Director | 4
6.5 | Responsibilities after termination or change of employment | People | Implemented - Not Reviewed | Training completion tracked in the LMS; completion rate above 95% for the last cycle. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | HR Director | 3
6.6 | Confidentiality or non-disclosure agreements | People | Implemented - Reviewed & Effective | Evidenced via signed employee handbook acknowledgement on file. |  | N/A - Maintain |  | HR Director | 4
6.7 | Remote working | People | Partially Implemented |  | Remote working policy exists but is not technically enforced (e.g. no device posture check). | Medium | 2026-12-30 | HR Director | 2
6.8 | Information security event reporting | People | Implemented - Reviewed & Effective | Evidenced via HR onboarding/offboarding checklist completion records. |  | N/A - Maintain |  | HR Director | 4
7.1 | Physical security perimeters | Physical | Implemented - Reviewed & Effective | Evidenced via access control system logs and the visitor register. |  | N/A - Maintain |  | Facilities Manager | 4
7.2 | Physical entry | Physical | Implemented - Reviewed & Effective | Verified during the last physical security walkthrough. |  | N/A - Maintain |  | Facilities Manager | 4
7.3 | Securing offices, rooms, and facilities | Physical | Implemented - Reviewed & Effective | Evidenced via facilities maintenance and inspection records. |  | N/A - Maintain |  | Facilities Manager | 4
7.4 | Physical security monitoring | Physical | Partially Implemented |  | CCTV covers the main entrance only; the server room and other secure areas are not monitored. | Medium | 2026-12-30 | Facilities Manager | 2
7.5 | Protecting against physical and environmental threats | Physical | Implemented - Reviewed & Effective | Evidenced via access control system logs and the visitor register. |  | N/A - Maintain |  | Facilities Manager | 4
7.6 | Working in secure areas | Physical | Implemented - Not Reviewed | Verified during the last physical security walkthrough. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Facilities Manager | 3
7.7 | Clear desk and clear screen | Physical | Implemented - Reviewed & Effective | Evidenced via facilities maintenance and inspection records. |  | N/A - Maintain |  | Facilities Manager | 4
7.8 | Equipment siting and protection | Physical | Implemented - Reviewed & Effective | Evidenced via access control system logs and the visitor register. |  | N/A - Maintain |  | Facilities Manager | 4
7.9 | Security of assets off-premises | Physical | Partially Implemented |  | No formal register of assets used off-premises; reliant on employee self-reporting. | Medium | 2026-12-30 | Facilities Manager | 2
7.10 | Storage media | Physical | Implemented - Reviewed & Effective | Verified during the last physical security walkthrough. |  | N/A - Maintain |  | Facilities Manager | 4
7.11 | Supporting utilities | Physical | Implemented - Reviewed & Effective | Evidenced via facilities maintenance and inspection records. |  | N/A - Maintain |  | Facilities Manager | 4
7.12 | Cabling security | Physical | Implemented - Not Reviewed | Evidenced via access control system logs and the visitor register. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Facilities Manager | 3
7.13 | Equipment maintenance | Physical | Implemented - Reviewed & Effective | Verified during the last physical security walkthrough. |  | N/A - Maintain |  | Facilities Manager | 4
7.14 | Secure disposal or re-use of equipment | Physical | Implemented - Reviewed & Effective | Evidenced via facilities maintenance and inspection records. |  | N/A - Maintain |  | Facilities Manager | 4
8.1 | User endpoint devices | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | IT Security Manager | 4
8.2 | Privileged access rights | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | IT Security Manager | 4
8.3 | Information access restriction | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | IT Security Manager | 4
8.4 | Access to source code | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | Head of Engineering | 4
8.5 | Secure authentication | Technological | Implemented - Not Reviewed | Automated control; evidenced via configuration export and the monitoring dashboard. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | IT Security Manager | 3
8.6 | Capacity management | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | IT Security Manager | 4
8.7 | Protection against malware | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | IT Security Manager | 4
8.8 | Management of technical vulnerabilities | Technological | Partially Implemented |  | Vulnerability scanning is performed quarterly; no formal SLA for remediation by severity. | Medium | 2026-12-30 | IT Security Manager | 2
8.9 | Configuration management | Technological | Not Implemented |  | No formal secure baseline configuration standard; configurations vary by engineer. | High | 2026-10-31 | IT Security Manager | 0
8.10 | Information deletion | Technological | Partially Implemented |  | Deletion occurs on request (e.g. DSAR) but there is no scheduled deletion against the retention schedule. | Medium | 2026-12-30 | IT Security Manager | 2
8.11 | Data masking | Technological | Not Implemented |  | No data masking applied to production data copied into test/staging environments. | High | 2026-10-31 | IT Security Manager | 0
8.12 | Data leakage prevention | Technological | Not Implemented |  | No data leakage prevention tooling in place; reliance on manual review and the acceptable use policy only. | High | 2026-10-31 | IT Security Manager | 0
8.13 | Information backup | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | IT Security Manager | 4
8.14 | Redundancy of information processing facilities | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | IT Security Manager | 4
8.15 | Logging | Technological | Implemented - Not Reviewed | Enforced via platform configuration; evidenced in the last technical control review. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | IT Security Manager | 3
8.16 | Monitoring activities | Technological | Not Implemented |  | No centralised security monitoring/SIEM capability; log review is manual and inconsistent. | High | 2026-10-31 | IT Security Manager | 0
8.17 | Clock synchronization | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | IT Security Manager | 4
8.18 | Use of privileged utility programs | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | IT Security Manager | 4
8.19 | Installation of software on operational systems | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | IT Security Manager | 4
8.20 | Networks security | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | IT Security Manager | 4
8.21 | Security of network services | Technological | Implemented - Not Reviewed | Verified via the most recent penetration test / vulnerability scan report. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | IT Security Manager | 3
8.22 | Segregation of networks | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | IT Security Manager | 4
8.23 | Web filtering | Technological | Partially Implemented |  | Web filtering is enabled for malware categories only; no policy-based category filtering. | Medium | 2026-12-30 | IT Security Manager | 2
8.24 | Use of cryptography | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | IT Security Manager | 4
8.25 | Secure development life cycle | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | Head of Engineering | 4
8.26 | Application security requirements | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | Head of Engineering | 4
8.27 | Secure system architecture and engineering principles | Technological | Implemented - Not Reviewed | Automated control; evidenced via configuration export and the monitoring dashboard. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of Engineering | 3
8.28 | Secure coding | Technological | Partially Implemented |  | Secure coding guidelines exist but are not enforced via automated code review or linting. | Medium | 2026-12-30 | Head of Engineering | 2
8.29 | Security testing in development and acceptance | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | Head of Engineering | 4
8.30 | Outsourced development | Technological | Implemented - Reviewed & Effective | Enforced via platform configuration; evidenced in the last technical control review. |  | N/A - Maintain |  | Head of Engineering | 4
8.31 | Separation of development, test, and production environments | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | Head of Engineering | 4
8.32 | Change management | Technological | Implemented - Reviewed & Effective | Verified via the most recent penetration test / vulnerability scan report. |  | N/A - Maintain |  | Head of Engineering | 4
8.33 | Test information | Technological | Implemented - Not Reviewed | Enforced via platform configuration; evidenced in the last technical control review. | Control operating; formal review/re-attestation not yet scheduled. | Low | 2027-02-28 | Head of Engineering | 3
8.34 | Protection of information systems during audit testing | Technological | Implemented - Reviewed & Effective | Automated control; evidenced via configuration export and the monitoring dashboard. |  | N/A - Maintain |  | Head of Engineering | 4
Formulas:
Target Remediation Date = IF([Priority]="N/A - Maintain","",Cover!$B6+INDEX('Reference Data'!$G2:G5,MATCH([Priority],'Reference Data'!$F2:F5,0)))

## Remediation Roadmap
Remediation Roadmap - Findings Requiring Action
Control ID | Control Name | Gap Description | Priority | Owner | Target Remediation Date | Status
5.21 | Managing information security in the ICT supply chain | ICT supply chain risk is not assessed separately from general supplier due diligence. | High | Vendor & Procurement Manager | 2026-10-31 | Not Started
5.28 | Collection of evidence | No documented procedure for collection and preservation of evidence following a security incident. | High | Security Operations Lead | 2026-10-31 | Not Started
5.30 | ICT readiness for business continuity | ICT continuity plan not yet aligned to BIA-derived recovery time/point objectives. | High | Head of GRC | 2026-10-31 | Not Started
5.7 | Threat intelligence | No formal threat intelligence process; ad hoc use of vendor security bulletins only. | High | Head of GRC | 2026-10-31 | Not Started
8.11 | Data masking | No data masking applied to production data copied into test/staging environments. | High | IT Security Manager | 2026-10-31 | Not Started
8.12 | Data leakage prevention | No data leakage prevention tooling in place; reliance on manual review and the acceptable use policy only. | High | IT Security Manager | 2026-10-31 | Not Started
8.16 | Monitoring activities | No centralised security monitoring/SIEM capability; log review is manual and inconsistent. | High | IT Security Manager | 2026-10-31 | Not Started
8.9 | Configuration management | No formal secure baseline configuration standard; configurations vary by engineer. | High | IT Security Manager | 2026-10-31 | Not Started
5.23 | Information security for use of cloud services | Cloud vendor security is reviewed at onboarding only; no ongoing cloud security governance process. | Medium | Head of GRC | 2026-12-30 | Not Started
5.35 | Independent review of information security | Last independent ISMS review was 19 months ago; no fixed review cadence is defined. | Medium | Head of GRC | 2026-12-30 | Not Started
6.7 | Remote working | Remote working policy exists but is not technically enforced (e.g. no device posture check). | Medium | HR Director | 2026-12-30 | Not Started
7.4 | Physical security monitoring | CCTV covers the main entrance only; the server room and other secure areas are not monitored. | Medium | Facilities Manager | 2026-12-30 | Not Started
7.9 | Security of assets off-premises | No formal register of assets used off-premises; reliant on employee self-reporting. | Medium | Facilities Manager | 2026-12-30 | Not Started
8.10 | Information deletion | Deletion occurs on request (e.g. DSAR) but there is no scheduled deletion against the retention schedule. | Medium | IT Security Manager | 2026-12-30 | Not Started
8.23 | Web filtering | Web filtering is enabled for malware categories only; no policy-based category filtering. | Medium | IT Security Manager | 2026-12-30 | Not Started
8.28 | Secure coding | Secure coding guidelines exist but are not enforced via automated code review or linting. | Medium | Head of Engineering | 2026-12-30 | Not Started
8.8 | Management of technical vulnerabilities | Vulnerability scanning is performed quarterly; no formal SLA for remediation by severity. | Medium | IT Security Manager | 2026-12-30 | Not Started

## Reference Data
Maturity Label | (unused) | Maturity Label | Score | Priority | Remediation Days
|  | Not Implemented | 0 | High | 60
|  | Ad Hoc | 1 | Medium | 120
|  | Partially Implemented | 2 | Low | 180
|  | Implemented - Not Reviewed | 3 | N/A - Maintain
|  | Implemented - Reviewed & Effective | 4